## Sheet1
Graphics
	TATexture					98
	TATextureManager					40			Release 1: Moving Player	Release 2: Menus	Release 3: Enemies	Release 4: Level Creation	Release 5: HUD	Release 6: Game!	Release 7: Pick-ups	Release 8: Bosses
	TAAnimation					121
	TAAnimationManager					51			TACamera	TAStateManager	SSEnemy	SSPlatform	TAFont	SSSandstorms	SSConsumable	SSMeleeBoss
	TAFont					50			TAGraphicsManager	TAState	SSMeleeEnemy(With AI)	SSLevelCreator	TAFontManager		SSHealthPickup	SSCasterBoss
	TAFontManager					40			SSCharacter	TAPurpose	SSWarrior		TASound		SSEnergyPickup
	TACamera					50			SSPlayer	TAProcessManager	SSBerserker		TASoundManager		SSArtifact
	TAGraphicsManager					20			TAApp	TAProcess	SSRangedEnemy(With AI)
					SSMain	SSScreen	SSCaster
Input					SSScreenManager	SSAttack
	TAKeys					41				SSEvent	SSMeleeAttack
	TAInputManager					37				SSEventManager	SSRangedAttack

Sound
	TASound					50			LOC: 170	LOC: 310	LOC: 260	LOC: 180	LOC: 180	LOC: 300	LOC: 60	LOC: 60
	TASoundManager					40

System
	TAStateManager					40
	TAState					15
	TAPurpose					10
	TAProcessManager					40
	TAProcess					50
	TAApp					15

Main game
	SSCharacter					20
		SSPlayer				50
		SSEnemy				20
			SSMeleeEnemy(With AI)			70
				SSWarrior		15
				SSBerserker		15
				SSMeleeBoss		15
			SSRangedEnemy(With AI)			70
				SSCaster		15
				SSCasterBoss		15
	SSPlatform					30
	SSLevelCreator					150
	SSConsumable					15
		SSHealthPickup				15
		SSEnergyPickup				15
		SSArtifact				15
	SSScreen					15
	SSScreenManager					60
	SSEvent					30
	SSEventManager					50
	SSMain					15
	SSAttack					15
		MeleeAttack				30
		RangedAttack				30
	SSSandstorms					300

					1898